## v1.0
Feature	Task	Priority	Orig Est (hrs)	Actual (hrs)	Remaining
Image Gallery	Make image info table in db	1	1.5	0	1.5		Time Estimate (hrs)	Total Time	Remaining Time
	send pic text from db to template	1	0.5	0	0.5		23	0	23
	“add text” tool for db manip.	2	1.25	0	1.25
HTTPS	learn how it works	2	2	0	2
	implement	1	1	0	1
Beautify Site	fix padding/margins	2	0.5	0	0.5
	round corners	1	0.5	0	0.5
	add color	2	1.5	0	1.5
	add decorations	3	2	0	2
	ASK CRISTEN	1	0.75	0	0.75
PUBLISH	Get server	1	2	0	2
	Host rbs	1	2	0	2
	Set URL	1	1	0	1
Login System	add db table for users	1	1	0	1
	add login to navbar	1	2	0	2
	autofill known fields from session in contact.html	1	0.5	0	0.5
CMS	make form for editing pic descriptions	1	2.5	0	2.5
	add form to gallery html	1	0.5	0	0.5

## v2.0
Feature	Task	Priority	Orig Est (hrs)	Actual (hrs)	Remaining
Enable Payments			1	0	1		Time Estimate (hrs)	Total Time	Remaining Time
Enable Payments			1	0	1		9	0	9
Enable Payments			1	0	1
Shopping Cart			1	0	1
Shopping Cart			1	0	1
Shopping Cart			1	0	1
Checkout			1	0	1		V2.0 table is rough outline; needs research
Checkout			1	0	1
Checkout			1	0	1		V2.0 table is rough outline; needs research

							V2.0 table is rough outline; needs research

							V2.0 table is rough outline; needs research